## 2022-23 HLA
Agreed HLA 2022-23
Site Ref | LDP | Site Name | Settlement | Location | Site Area (ha's) | Company/Landowner | Developer Type | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033+ | Built | U/C | Remain | Total | Permission/Status | Main Application Ref No's | Decision
[8 empty] | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Year 10+
265 | H01 | Sunnyside | Alloa | Forth | 4.27 | Mulraney Group | Private |  |  |  | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 110 |  | X | 320 | 320 | LDP Site | n/a | n/a
263 | H03 | Carsebridge Road North | Alloa | Forth | 7.44 | Advance Construction | Private | 2026/27 Year 4: 30; 2027/28 Year 5: 30; 2028/29 Year 6: 30 |  | X | 90 | 90 | Application submitted | 21/00069/PPP | Pending
284 | H04 | Carsebridge | Alloa | Forth | 17.29 | Advance Construction | Private |  |  | 20 | 60 | 60 | 60 | 60 | 60 | 60 | 20 |  |  | X | 400 | 400 | Application submitted | 21/00069/PPP | Pending
260 | H08 | Earlsfield West (Phase 9) | Alloa | Forth | 4.3 | Allanwater Developments | Private | 2023/24 Year 1: 7; 2024/25 Year 2: 36; 2025/26 Year 3: 48 | 0 | 7 | 84 | 91 | Under construction | 21/00107/FULL | Approved at Appeal
246 | H10 | Central Parkland | Alloa | Forth | 1.02 | Clackmannanshire Council | Council | 2025/26 Year 3: 19; 2026/27 Year 4: 19 |  | X | 38 | 38 | LDP Site
266 | H14 | Paton's Bowling Club | Alloa | Forth | 1.58 | Mulraney Group | Private | 2026/27 Year 4: 20; 2027/28 Year 5: 20; 2028/29 Year 6: 10 |  | X | 50 | 50 | LDP Site | n/a | n/a
245 | H15 | Former FV College | Sauchie | Forth | 5.42 | Ediston Homes | Private | 2023/24 Year 1: 43; 2024/25 Year 2: 10 | 84 | 40 | 13 | 137 | Under construction | 14/00254/FULL 17/00241/MSC | Approved Approved
244 | H16 | Sauchie West | Sauchie | Forth | 52.81 | Allanwater Developments | Private |  |  |  | 30 | 75 | 75 | 75 | 75 | 75 | 75 | 520 |  | X | 1000 | 1000 | LDP Site | 10/00153/PPP 23/00219/MSC | Approved at Appeal Pending
227 | H23 | The Manse, Main Street | Sauchie | Forth | 0.1 | Grattan and Hynds | Private | 2027/28 Year 5: 4 |  | X | 4 | 4 | Expired Permission | 06/00308/FULL 09/00216/PPP | Approved Approved
278 | - | Schawpark Golf Club | Sauchie | Forth | 0.45 | Schawpark Golf Club | Private | 2025/26 Year 3: 25; 2026/27 Year 4: 25; 2027/28 Year 5: 25; 2028/29 Year 6: 15 |  | X | 90 | 90 | Planning Application Planning Application Planning Application | 19/00173/FULL 21/00294/FULL 21/00295/FULL | Approved Approved Approved
237 | H26 | Muirside, Lethen View | Tullibody | Forth | 0.39 | Glenview Projects Limited | Private | 2023/24 Year 1: 7 | 0 | 2 | 5 | 7 | Planning Permission | 21/00266/FULL | Approved
151 | H27 | Main Street/North Street | Clackmannan | Forth | 0.1 | Kingdom Housing Association/ Clackmannanshire Council | Housing Assoc. | 2024/25 Year 2: 5 |  | X | 5 | 5 | LDP Site | 20/00215/FULL | Approved
249 | H28 | Helensfield | Clackmannan | Forth | 6.57 | Premier Properties | Private | 2025/26 Year 3: 15; 2026/27 Year 4: 15; 2027/28 Year 5: 15; 2028/29 Year 6: 10 |  | X | 55 | 55 | LDP Site
289 | - | Lochies Road | Clackmannan | Forth | 0.19 | Clackmannanshire Council | Council | 2023/24 Year 1: 8 |  | X | 8 | 8 | SHIP
250 | H32 | Lornshill Steading | Countryside | Forth | 0.84 | Mr Robert Petrie | Private | 2025/26 Year 3: 6; 2026/27 Year 4: 12 |  | X | 18 | 18 | Planning Permission | 09/00144/FULL | Approved
282 | H33 | Ditch Farm | Countryside | Forth | 1.07 | J Gilvear and Sons | Private | 2027/28 Year 5: 5; 2028/29 Year 6: 5 |  | X | 10 | 10 | LDP Site
280 | - | Pitfairn Road/Burnee | Fishcross | Forth | 0.25 | Mrs Sandra Vaughan | Private | 2023/24 Year 1: 2 | 2 | 2 | 0 | 4 | Planning Permission | 15/00176/FULL | Approved
248 | H34 | Middletonkerse | Menstrie | West Ochils | 9.25 | Mr R Muirhead | Private | 2027/28 Year 5: 20; 2028/29 Year 6: 20; 2029/30 Year 7: 20; 2030/31 Year 8: 20; 2031/32 Year 9: 4 |  | X | 84 | 84 | LDP Site
258 | H36 | Mains Farm Steading | Menstrie | West Ochils | 0.65 | Mr R Muirhead | Private | 2028/29 Year 6: 8 |  | X | 8 | 8 | LDP Site
179 | H37 | Brook Street/Beauclerc Street | Alva | West Ochils | 1.05 | Hillfoot Homes | Private | 2025/26 Year 3: 17 |  | X | 17 | 17 | Planning Permission | 15/00128/FULL | Approved
286 | H42 | Alva West | Alva | West Ochils | 12.61 | Allanwater Developments | Private | 2025/26 Year 3: 36; 2026/27 Year 4: 40 |  | X | 76 | 76 | LDP Site | 22/00187/FULL | Refused
146 | H43 | Lower Mill Street | Tillicoultry | West Ochils | 10.04 | Kingdom Housing Association | Housing Assoc. | 2025/26 Year 3: 50; 2026/27 Year 4: 24 |  | X | 74 | 74 | Planning Permission | 10/00036/MSC 19/00179/FULL 20/00204/FULL | Approved Approved Approved
273 | H44 | Middleton Mill/Upper Mill Street | Tillicoultry | West Ochils | 1.09 | Tillicoultry Quarries | Private | 2028/29 Year 6: 25; 2029/30 Year 7: 25 |  | X | 50 | 50 | LDP Site
290 | - | Park Street | Tillicoultry | West Ochils | 0.41 | Kingdom Housing Association | Housing Assoc. | 2025/26 Year 3: 8 |  | X | 8 | 8 | SHIP | 22/00234/FULL | Approved
132 | H45 | Coalsnaughton North | Coalsnaughton | West Ochils | 10.75 | Kudos Partnership | Private/Council |  |  |  | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 |  | X | 240 | 240 | LDP Site | 20/00267/PPP | n/a
275 | H47 | Dollar Settlement Expansion (South) |  |  |  | PPCA | Private | 2025/26 Year 3: 20; 2026/27 Year 4: 30; 2027/28 Year 5: 40; 2028/29 Year 6: 40; 2029/30 Year 7: 40; 2030/31 Year 8: 40 |  | X | 210 | 210 |  | 18/00283/PPP | Pending
275 | H47 | Dollar Settlement Expansion (East) | Dollar | East Ochils | 33.49 | Colliers | Private | 2025/26 Year 3: 20; 2026/27 Year 4: 35; 2027/28 Year 5: 35; 2028/29 Year 6: 35; 2029/30 Year 7: 35; 2030/31 Year 8: 15 |  | X | 175 | 175 |  | 18/00283/PPP | Pending
291 | H48 | Dollar Golf Club | Dollar | East Ochils | 0.05 | Harviestoun Estate | Private | 2027/28 Year 5: 5 |  | X | 5 | 5 | Expired Permission | 10/00227/FULL | Approved
276 | H49 | South and East of Pool of Muckhart | Muckhart | East Ochils | 6.64 | Springfield Homes | Private/ Housing Assoc. | 2023/24 Year 1: 12; 2024/25 Year 2: 24; 2025/26 Year 3: 14 | 0 | 10 | 40 | 50 | LDP Site | 19/00148/FULL | Appeal Allowed
276 | H49 | South and East of Pool of Muckhart | Muckhart | East Ochils | 6.64 | Kingdom Housing Association | Housing Assoc. | [15 empty] | LDP Site | 19/00148/FULL | Appeal Allowed
276 | H49 | South and East of Pool of Muckhart | Muckhart | East Ochils | 6.64 | Tim Allan | Private | [13 empty] | 0 | 0 | LDP Site | 19/00148/FULL | Appeal Allowed
252 | H50 | Forestmill | Forestmill | East Ochils | 121.65 | Hermiston Securities | Private |  |  |  |  | 25 | 25 | 25 | 25 | 25 | 25 | 1100 |  | X | 1250 | 1250 | Planning Permission | 06/00283/OUT 14/00250/MSC 16/00144/FULL | Approved Approved Approved
228 | H51 | Solsgirth | Countryside | East Ochils | 5.71 | EMA Architecture + Design | Private | 2024/25 Year 2: 15; 2025/26 Year 3: 15; 2026/27 Year 4: 15 |  | X | 45 | 45 | LDP Site | 09/00188/FULL 19/00272/FULL | Approved Pending
[8 empty] | 79 | 90 | 313 | 415 | 419 | 418 | 340 | 295 | 224 | 180 | 1760 | 86 | 61 | 4472 | 4619
[8 empty] | 2023/24 Year 1: 1316; 2028/29 Year 6: 1457; 2033+ Year 10+: 1760 | 86 | 61 | 4472 | 4619
[8 empty] | 2023/24 Year 1: 2773; 2033+ Year 10+: 1760 | 86 | 61 | 4472 | 4619

## 2022-23 HLA Table
Year | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033+
Completions | 79 | 90 | 313 | 415 | 419 | 418 | 340 | 295 | 224 | 180 | 1760